Annex 3: Template for Process Action Plan (PAP) for Programmes and Stand-alone Projects between DKK 20-100 million

The table below should be read as an illustrative example of how a process action plan for the quality assurance and approval process may look. It may serve as a template to be amended as needed for the individual process.

Templates for Process Action Plans are divided in the following thresholds: 3.1) Above DKK 100 million, 3.2) Between DKK 20-100 million, and 3.3) below and including DKK 20 million. If a grant between DKK 20-100 million is concluded as ‘high risk’ on the kick-off meeting, the template for PAP for programmes and Stand-alone Projects above DKK 100 million should be applied.

B) Programme and Stand-alone Project between DKK 20-100 million

|  | Action | Deadlines | Responsible / involved parties | Approx. duration in weeks |
| --- | --- | --- | --- | --- |
| 1 | Identification and PAP |  |  |  |
|  | Recruit consultants for the identification process if found needed (ToR, tender if needed and contracting) | Set by unit depending on the date for submitting documents to LÆRING for the kick off meeting | Unit | From 3 to 8 weeks depending on the procurement process |
|  | Identification process to produce/update background analysis/assessments/studies, political economy analysis/context assessment, any other preparatory analyses needed, reflect and document on experience and lessons learned. Establish taskforce if relevant. |  | Unit with consultants if found necessary | 8-12 weeks |
| 2 | Identification Note (2 pager) |  |  |  |
|  | On basis of the identification process, draft the Identification Note including risk annex (use template for 2 pager) |  |  |  |
|  | Process Action Plan (PAP) for the process is updated. |  |  |  |
| 3 | Kick-off meeting |  |  |  |
|  | Notify LÆRING on selected date for the kick off meeting | Latest two weeks prior to the kick off meeting (10 working days) | Unit |  |
|  | Submit Identification Note and PAP to LÆRING | One week prior to kick off meeting (five working days) | Unit |  |
|  | Kick-off meeting conducted |  | LÆRING, TILSKUD, AFRPOL (and relevant invited units/embassies) |  |
|  | If it is concluded on the kick-off meeting that the programme/project is ‘high risk’ please refer to the PAP for programmes and Stand-alone Projects above DKK 100 million | After kick-off meeting | Unit |  |
|  | Minutes from kick off meeting | LÆRING distributes final minutes one week after meeting. | LÆRING |  |
|  | Draft ToR for recruitment of formulation (process) consultants (if applicable). |  | Unit |  |
| 4 | Formulation of draft programme and project document |  |  |  |
|  | Tender and recruitment of formulation (process) consultants (if applicable). Could also include further analysis if needed, decide on method for selection of projects and partners etc. |  | Unit | From 3 to 8 weeks depending on the procurement process |
|  | Formulation of draft programme and project documents based on the identification phase, Identification Note and minutes from kick off meeting, field visits, partner consultation etc. |  | Unit | 6 weeks |
|  | Draft and finalise ToR for external appraisal |  | Unit | 1-2 weeks |
| 5 | Quality assurance: External Appraisal |  |  |  |
|  | Tendering for and contracting of external appraisals consultants |  | Unit | From 3 to 8 weeks depending on the procurement process |
|  | External Appraisal |  | External consultants | 4-5 weeks |
| 6 | Finalising of PD and approval |  |  |  |
|  | Incorporating and reflecting on recommendations and comments from external appraisal. |  |  | 1 week |
|  | Insert unit’s response to summary of recommendations from external appraisal |  | Unit |  |
|  | Submission for State Secretary for development policy for approval via the distribution group ‘Bevillingssekretariatet’ as second approver. Subsequently, LÆRING facilitates the Minister’s final approval. |  | Unit & Bevillingssekretariatet (LÆRING) |  |
|  | Document for Finance Committee (‘Aktstykke’) and presentation to the Parliamentary Finance Committee (if applicable) |  | Unit |  |
| 7 | Initial actions following approval |  |  |  |
|  | LÆRING facilitates that approved grants are published on Danida Transparency after the Minister’s final approval | 3-5 working days after approval | Bevillingssekretariatet (LÆRING) |  |
|  | Signing of Government-to-Government agreement(s) and/or other legally binding agreements (commitments) with partner(s) | After the Minister’s approval | Unit |  |
|  | Register commitment(s) in MFA’s financial systems within the planned quarter | After agreement(s) are signed | Unit |  |