Template for Process Action Plan (PAP) for Programmes and Stand-alone Projects DKK 100 million and above

The table below should be read as an illustrative example of how a process action plan for the quality assurance and approval process may look. It may serve as a template to be amended as needed for the individual process.

Templates for Process Action Plans are divided in the following thresholds: A) DKK 100 million and above, B) Above DKK 20 to 99 million, and C) below and including DKK 20 million. If a grant between DKK 20-99 million is concluded as ‘high risk’ on the kick-off meeting, the template for PAP for programmes and Stand-alone Projects DKK 100 million and above should be applied.

A) Programmes and Stand-alone Projects DKK 100 million and above

|  | Action | Deadlines | Responsible / involved parties | Approx. duration in weeks |
| --- | --- | --- | --- | --- |
| 1 | Identification and PAP |  |  |  |
|  | Recruit consultants for the identification process if found needed (ToR, tender if needed and contracting) |  | Unit | From 3 to 8 weeks depending on the procurement process |
|  | Identification process to produce/update background analysis/assessments/studies, political economy analysis/context assessment, any other preparatory analyses needed, reflect and document on experience and lessons learned. Establish taskforce if relevant. |  | Unit with consultants if found necessary | 8-12 weeks |
| 2 | Identification Note (2 pager) |  |  |  |
|  | On basis of the identification process, draft the Identification Note including risk annex (use template for 2 pager) |  |  |  |
|  | Process Action Plan (PAP) for the process is updated. |  |  |  |
| 3 | Kick-off meeting |  |  |  |
|  | Notify LÆRING on selected date for the kick off meeting | Latest two weeks prior to the kick off meeting (ten working days) | Unit |  |
|  | Submit Identification Note, self-risk assessment annex and PAP to LÆRING | One week prior to kick off meeting (five working days) | Unit |  |
|  | Kick-off meeting conducted |  | LÆRING, TILSKUD, AFRPOL (and relevant invited units/embassies) |  |
|  | Minutes from kick off meeting | LÆRING distributes final minutes one week after meeting. | LÆRING |  |
| 4 | Formulation of draft programme and project documents |  |  |  |
|  | Tender and recruitment of formulation (process) consultants (if applicable), including drafting of ToR. Could also include further analysis if needed, decide on method for selection of projects and partners etc. |  | Unit | From 3 to 8 weeks depending on the procurement process |
|  | When formulation process has been initiated - organise meeting with LÆRING development specialist responsible for pre-appraisal |  | Unit | 6 weeks |
|  | Formulation of early draft programme and project documents based on the identification phase, Identification Note and minutes from kick off meeting, field visits, partner consultation etc. |  | Unit |  |
| 5 | Quality assurance (early appraisal) and public consultation |  |  |  |
|  | Draft and finalise ToR for early appraisal forwarded to LÆRING |  | Unit/ LÆRING | 2 weeks |
|  | Tendering for and contracting of early appraisal consultants |  | LÆRING | From 3 to 8 weeks depending on the procurement process |
|  | Forward early draft PD to LÆRING for appraisal and public consultation |  | Unit | 8 weeks |
|  | Early-appraisal incl. preparation, field visits and reporting |  | LÆRING |  |
| 6 | External Panel |  |  |  |
|  | Documentation for meeting in External Panel forwarded to members via ‘Bevillingssekretariatet’ in LÆRING: Documentation includes: - Appropriation Cover Note(s) - Early draft Programme and project documents - Early-appraisal recommendations | 2 weeks prior to meeting | Unit to LÆRING | 4-5 weeks from sent documentation to minutes |
|  | Meeting in External Panel |  |  |  |
|  | Minutes from External Panel | LÆRING distributes final minutes two weeks after meeting. | LÆRING & External Panel |  |
| 7 | Finalising of PD |  |  |  |
|  | Incorporating and reflecting on recommendations and comments from responses to public consultation, pre-appraisal and External Panel in PD and finalising PD |  | Unit | 4 weeks |
|  | Final PD, annexes, appropriation cover note, summary of recommendations from pre-appraisal incl. unit’s response and summary of recommendations from External Panel incl. unit’s response forwarded to LÆRING for desk verification |  | Unit |  |
|  | Desk verification by LÆRING |  | LÆRING | 1 week |
| 8 | Approval |  |  |  |
|  | Submission for State Secretary for development policy for approval via the distribution group ‘Bevillingssekretariatet’ as second approver. Following LÆRING facilitates the Minister’s approval. |  | Unit & Bevillingssekretariatet (LÆRING) | 1-2 weeks |
|  | Document for Finance Committee (‘Aktstykke’) and presentation to the Parliamentary Finance Committee (if applicable) |  | Unit |  |
| 9 | Initial actions following the Minister’s approval |  |  |  |
|  | LÆRING facilitates that approved grants are published on Danida Transparency after the Minister’s approval | 3-5 working days after approval | Bevillingssekretariatet (LÆRING) |  |
|  | Signing of Government-to-Government agreement(s) and/or other legally binding agreements (commitments) with partner(s) | After the Minister’s approval | Unit |  |
|  | Register commitment(s) in MFA’s financial systems within the planned quarter | After agreement(s) are signed | Unit |  |

An early appraisal is an appraisal of an early version of the draft programme and project documents.