Template for Stand-Alone MFA Project Documents

Part A: 	Template for the Project Document

Part B: 	Guidance for the Template

Part A: Template for Stand-Alone Project Documents

Appropriation Cover Page

Follow format for projects (under revision)

Project Cover Page

The cover page should mention:

- Ministry of Foreign Affairs of Denmark

- Project full title and period

- P360 number

- Draft/Final project document

- Date of document version

Standard Table of Content

- Introduction

- Project objective and key features

- Project context

- Rationale and justification of support

- Theory of Change and key assumptions

- Summary of results framework

- Project budget and financial management

- Project management, monitoring and reporting

- Project risk management

Annexes

Annex A- MFA Partner assessment

Annex B- MFA Results framework

Annex C- MFA Budget details

Annex D- MFA Risk management matrix*

Annex E- MFA context analysis*

Annex F- Option 1) Partners Project description based on existing project documentation or Option 2) Template for project description provided to the partner by MFA

Annex G-MFA Process Action Plan

* Annex D and E are not mandatory for projects up to and including DKK 20 million.

- Introduction

The present MFA Project Document describes the Danish development cooperation contribution to [name of project], implemented by [name of partner] for the period [Danish support timeframe]. The MFA unit responsible for the project is [MFA unit such as Embassy of Denmark in [capital] or HQ unit in the Ministry of Foreign Affairs of Denmark].

The Danish contribution to the project takes the form of [support modality noted in the project document].

This project document and its annexes, including partner documentation and annexes are an integral part of the legal bilateral agreement between the MFA and the implementing partner.

- Project objective and key features

Based on the project documentation enclosed in Annex F, the MFA unit must summarise the key features of the project, with focus on the areas of interest from Denmark’s perspective:

- The project objective and outcomes

- The total budget, target group(s) and geographic coverage

- The period of the project (Danish contribution) and of the partner’s initiative/strategic plan, if different

- Project context

Based on the MFA context analysis (Annex E), summarise the specific context of the project with focus on:

- The country, region, thematic area and/or sector(s) relevant to the proposed areas of intervention

- The issue(s) the project will focus on and proposed entry point(s)

- The choice of the target group and geographic areas of intervention

- Considerations on poverty orientation and rights-based principles

- Rationale and justification of support

The responsible MFA unit (not the partner) must explain why it is relevant for Denmark to support this project in terms of:

- Danish development policy and other strategic priorities or interests (e.g., economic diplomacy)

- Responsiveness to specific global/regional/national/local priorities and policies as expressed by the targeted countries or stakeholders, and to their context

- Complementarity with other Danish development cooperation instruments

- Added value to and coordination with similar development cooperation initiatives

- In case of climate tagging, the choice of the Rio marker should be clearly justified in line with MFA guidance

- The modality of support including considerations made with regard to ownership and local leadership

Choice of partner

- Based on the partner assessment (Annex A), summarise the partner’s capacity and performance a) to deliver results and b) to manage funds, monitor and report, including previous experience and lessons as relevant

- Enclose the MFA-led partner assessment in Annex A with documentation to demonstrate the partner’s capacity. If the partner is to be selected during implementation (e.g., call for proposal or procurement), describe the selection method, process and criteria in Annex B.

- Theory of Change and key assumptions

- Based on the partner documentation in Annex F including the Theory of Change, explain how key outcomes and underlying key outputs funded or prioritised by Denmark are expected to contribute to the project’s objective(s), presenting the change pathways for each key outcome.

- Based on the ToC included in Annex F, highlight the key assumptions that must hold a) for the project to achieve these key outputs, and b) for these outputs to yield the desired key outcomes of the Danish contribution

- Explain how sustainability is considered

- Summary of results framework

Based on Annex F, present the project results framework either in full or in summarised form (enclosing a detailed results framework in Annex B).

This should focus on the project’s objective, key outcome(s) and corresponding outputs and indicators that the MFA will be monitoring and reporting on in RFI. Outputs and indicators should only present the overall outputs under a given outcome (e.g., only the level of output 1.1 under outcome 1, not lower level outputs output 1.1.1). Include the detailed version of the MFA results framework for the Danish contribution in Annex B, including lower level outputs if relevant, and baselines and targets.

Note: If the Danish project support is (softly) earmarked for selected project change pathways/results chains/outcomes, these should be the focus of the results framework summary.

- Project budget and financial management

Based on the detailed budget in Annex C, summarise the overall budget of the Danish contribution including overhead costs and other budget lines (e.g., contingencies, audits).

For climate tagged projects, reflect this in the budget. The relevant budget lines should be clearly marked.

- For core contributions (including soft earmarking or pooled funds) present the full budget of the supported initiative/strategic plan, and contributions from other donors

- Explain the partner’s financial and audit arrangements, potential risks, and how any deviations (e.g., with multi-bi support) from the MFA’s Financial Management Guidelines (FMG) will be addressed

- Project management, monitoring and reporting

- Summarise the MFA organisational set-up of the project

- Explain how the MFA unit will be involved in the governance structure and have influence on decision-making, especially in case of multi-bi support

- Explain the MFA unit’s approach to monitoring the project (financial, technical) and how it will engage in dialogue with the partner and other stakeholders involved in implementation, as well as coordination fora as relevant (as reflected in the Process Action Plan for the implementation phase).

- Show the reporting frequency/schedule and explain any deviations from FMG

- Risk management

- Based on the risks elaborated in Annex F by the partner, highlight key risks foreseen from the perspective of the MFA including any risks not addressed by the partner.

- Explain how the MFA will identify and manage these risks if they materialise, possibly using scenario planning

Part B: Guidance for Standard Template for Stand-Alone Project Documents

The purpose of this document is to guide MFA units in preparing the MFA project document for stand-alone projects in line with the Aid Management Guidelines (AMG) for Bilateral Cooperation.

Projects which form part of an overarching programme should use the Template for Programme Documents and Underlying Projects.

A stand-alone project is implemented by one partner, spanning non-governmental and governmental organisations, multilateral organisations and international organisations on the OECD/DAC list.

The project document shall be drafted by the responsible MFA unit based on the partner documentation provided in Annex F.

The length of the stand-alone MFA project document should proportionate to the project’s size and complexity, but as a general rule, it should be around 5 pages (and not exceed 10 pages) excluding annexes.

The stand-alone project document serves the following purposes:

| Purpose | Documents to be enclosed |
| --- | --- |
| Basis for appraisal | For projects subject to external appraisal - Project appropriation cover note - MFA project document (final draft) - Annexes including partner documentation |
|  | For projects subject to early appraisal - Project appropriation cover note - early draft MFA project document with annex E, annex G, and (early) partner project documentation (with annexes). If drafted, partner assessment, MFA results framework, MFA budget at outcome level, and MFA risk management matrix should be submitted |
| Basis for submission to External Panel (as applicable) | - Project appropriation cover note - Early draft MFA project document and annex F (partner project document) |
| Basis for approval process | - Project appropriation cover note - MFA project document - Annexes including partner documentation |
| Basis for partner agreement | - MFA project document - Annexes including partner documentation |

When the MFA supports a partner initiative through direct award, the following annexes should be for drafted by the MFA and the partner respectively:

| For support through direct award: | Annexes to stand-alone project document |
| --- | --- |
| Produced by MFA | - Project appropriation cover note - MFA context analysis - MFA partner assessment - MFA results framework - MFA project budget - MFA risk management matrix |
| Produced by partner | - Project documentation as presented in partner documentation, i.e., programme/project document/ strategic plan, including partner’s context analysis, ToC, results framework, budget, management set-up, MEAL set-up, risk management etc. etc. - Risk management matrix - Input to MFA budget details |

The project document should not be a copy of the partners’ documentation in Annex F. It is a summary document based on the partner’s own project description but focused on the Danish perspective and management of the contribution.

If the project is supporting a partner that does not have a format to describe its initiative, and the partner requests a template, the standard template for project description can be used as Annex F (Option 2). If the partner wishes to use their own template, this is acceptable as long as it provides the information needed as outlined in the standard template for project description.

For projects of 20 million and below, a simplified procedure can be followed. In this case, separate context analysis documents and risk analysis matrixes should not be produced by the MFA unit. These elements should however form an integral part of the MFA product document as well as the underlying partner documentation.

If a procurement process is envisaged (e.g., a fund manager to be identified after formulation and appraisal), the MFA unit should produce the same documents as for a direct award expect for the partner assessment. In addition, the MFA unit will produce the tender material. Please consult ØKO if needed.

| For Procurement: | Annexes to stand-alone project document |
| --- | --- |
| Produced by MFA | - Project appropriation cover note - MFA project document - Annexes minus partner assessment - Tender material |
| Produced by partner | Project documentation as responds to the tender |

In case of a Management Unit or delegated cooperation with the MFA as lead, the MFA unit should produce the same documents for the appraisal as for direct award and procurement. This includes the MFA project document and relevant annexes.

If grant support is to be awarded through a Call for Proposal (CfP), a draft CfP information note must be formulated and submitted for appraisal instead of a MFA project document. The MFA unit still needs to produce a context analysis and a results framework (outcome level). A partner assessment should not be produced. Please refer to the Guidelines for Selection of Grant Recipients (including Calls for Proposals and template for the information note). Consult TILSKUD if needed.

| For Call for proposals: | Annexes to information note |
| --- | --- |
| Produced by MFA | - Project appropriation cover note - Information Note (see template for CfP information note) - Context analysis - Results framework (outcome level) - MFA risk management matrix (to be drafted based on selected project proposal) |
| Produced by partner | Project documentation as a response to CfP |

Please consult the Aid Management Guidelines for Bilateral Cooperation for more details on the appraisal [Bilateral cooperation] and the Guidelines for approval of bilateral (incl. multi-bi) projects and programmes for approval processes.

Max. 1 sentence for publication on OpenAid. It is typically the partner’s project objective, unless we are earmarking to specific outcomes or outputs. The key outcomes should indicate the outcomes supported by the Danish contribution.

The table for justifying the Rio marker scoring under Annex C – MFA Project budget details should be completed in this case.