Annex G: Template for Process Action Plan (PAP) for Stand-alone Projects DKK 20 million and below

The table below should be read as an illustrative example of how a process action plan for the quality assurance and approval process may look. It may serve as a template to be amended as needed for the individual process.

Templates for Process Action Plans are divided in the following thresholds: A) DKK 100 million and above, B) From DKK 20 to 99 million, and C) below and including DKK 20 million. If a grant between DKK 20-99 million is concluded as ‘high risk’ on the kick-off meeting, the template for PAP for programmes and Stand-alone Projects DKK 100 million and above should be applied.

C) Stand-alone Projects below and including DKK 20 million

|  | Action | Deadlines | Responsible / involved parties | Approx. duration in weeks |
| --- | --- | --- | --- | --- |
| 1 | Identification and PAP |  |  |  |
|  | Recruit consultants for the identification process if found needed (ToR, tender if needed and contracting). |  | Unit | From 3 to 8 weeks depending on the procurement process |
|  | Identification process to produce/update background analysis/assessments/studies, political economy. analysis/context assessment, any other preparatory analyses needed, reflect and document on experience and lessons learned. |  | Unit with consultants if found necessary | 2 weeks |
| 2 | Formulation and finalisation of draft project document |  |  |  |
|  | If needed, include further analysis, decide on method for selection of projects and partners etc. |  | Unit | 4 weeks |
|  | Finalise the PD for internal (unit) quality assurance. |  | Unit |  |
| 3 | Quality assurance: Internal Quality Assurance Checklist |  |  |  |
|  | The unit conducts the quality assurance with the template Annex I “Quality Assurance Checklist”. |  | Unit | 1 week |
| 4 | Approval |  |  |  |
|  | Submission for the Head of department’s approval for grants up to DKK 10 million. For grants above DKK 10 million, submission to State Secretary for development policy for approval via the distribution group ‘Bevillingssekretariatet’ as second approver. Subsequently, LÆRING facilitates the Minister’s final approval. |  | Unit | 1 week |
| 5 | Initial actions following approval |  |  |  |
|  | Signing of Government-to-Government agreement(s) and/or other legally binding agreements (commitments) with partner(s). | After approval | Unit |  |
|  | Register commitment(s) in MFA’s financial systems within the planned quarter. | After agreement(s) are signed | Unit |  |