Template for Process Action Plan (PAP) for Projects above 39 mill. DKK

| Action/product | Deadlines | Responsible/involved Person and unit | Comment/status |
| --- | --- | --- | --- |
| The programme budget is approved | Min. 14 months prior to the minister’s approval of the programme | Responsible: Person/unit Involved: Person/unit |  |
| Identification, concept note and programme committee |  |  |  |
| Process Action Plan. Addressing planning of design, formulation, appraisal and approval. | Min. 14 months prior to the minister’s approval | Responsible unit in consultation with partner and TQS | Consult PAP with Partner and TQS PAP should as needed include budget for external consultant to support the process. |
| Analysis of context, id. of partners and engagements, | Min. 13 months prior to the minister’s approval | Responsible unit in consultation with partner. Consultant contracted as needed | An external consultant can be of major support for responsible units at embassies and HQ in the preparation of the initial analysis and concepts and in the formulation of the programme document. |
| Draft Concept note and annexes | Min. 11 months prior to the minister’s approval | Responsible Unit in dialogue with partner. Support from consultant as needed. | Early dialogue with partner can save time in the end and increase probability of ownership. |
| Forward Concept note and annexes to TQS Public consultation of Concept note. | 17 days in advance of meeting in Danida Programme Committee | Responsible unit |  |
| Meeting in Danida Programme Committee. List of received responses from the consultation and summary conclusions from Danida Programme Committee. | Min. 10 months prior to the minister’s approval of the programme | TQS and responsible unit |  |
| Formulation |  |  |  |
| Initiate development of Programme Documents (and if relevant Development engagement Documents) | Min. 10 months prior to the minister’s approval of the programme | Responsible unit in cooperation with partner and as needed supported by consultant. |  |
| Draft Programme Document (and if relevant Development Engagement Document) | 9 months prior to the minister’s approval of the programme | Responsible unit in consultation with partner |  |
| Appraisal |  |  |  |
| Request for appraisal forwarded to TQS including: Draft TOR for appraisal, revised draft PAP and Draft Program Document (if relevant incl. Development engagement Documents) and associated partner documentation | Min 10 months prior to the minister’s approval of the programme | Responsible unit | Initiate appraisal process as early as possible. Tendering requires a set of terms of reference only and can be initiated, while formulation is still on-going- This will save time. |
| Tender for consultants initiated | Min. 9-10 months prior to the ministers approval of the programme | TQS/ØKO |  |
| Contract with consultant | 8 months | TQS/ØKO |  |
| Mobilization time for consultant | 7 months |  |  |
| Appraisal initiated | 6 months prior to the Ministers approval of the programme | TQS |  |
| Draft Appraisal Report including summary of conclusions and recommendations | Min. 5 months prior to the minister’s approval of the programme | TQS |  |
| Final appraisal report integrating comments from responsible unit and partner | 4 months prior to the Minister’s approval of the programme |  |  |
| Final Programme Document, annexes and Development engagement Documents forwarded to TAS | Min. 13 working days before meeting in Council for Development Policy | Responsible Unit |  |
| Presentation to the Council for Development Policy | Min. 2 months prior to the Minister’s approval of the programme | Responsible unit |  |
| The minister approves the programme | After Council for Development Policy meeting |  |  |
| Document for Finance Committee (Aktstykke) If direct legal basis for the commitment is not in place at Finance Act: Presentation to the Parliamentary Finance Committee | After Minister’s approval |  |  |
| Signing of Government-to-government agreement(s) and/or other legally binding agreements (commitments) with partner(s) | After Minister’s approval |  |  |
| Register commitment in MFA’s financial systems within budgeted quarter. | After agreement(s) are signed |  |  |